## Read me
M365 Hardening Kit: Emergency Top 10
Version | 1.0
What this is | The same backlog as the Jira CSV, as a project plan for teams without Jira. One row per control on 'Project plan'; 'Dashboard' shows progress.
Your cells | Yellow cells on 'Project plan': Owner, Start, Due, Status, Done date, Notes. Everything else is filled in or calculated.
Status values | To do, In progress, Blocked, Done, Not applicable. Pick from the drop-down.
% complete | Done = 100%. In progress = 50% (assumption: a simple midpoint, so the dashboard moves before a control is finished). Everything else = 0%. 'Not applicable' rows are left out of the totals.
Effort (h) | Hands-on hours from the guide: upper end of a range, minutes converted to hours. Waiting time (DNS, rollout weeks, recurring reviews) is not included.
Overdue | Due date before today and status not Done or Not applicable.
Example row | Owner: j.doe · Start: 03/11/2026 · Due: 07/11/2026 · Status: In progress · Done date: (empty until Done) · Notes: Report-only since 03/11, review on 06/11.
Details per control | Why, steps, read-only check, verify, licence and sources are in the guide (.md) that ships in the same zip.
Disclaimer | Not affiliated with or endorsed by Microsoft. Test every change in Report-only or on a pilot group first.

## Dashboard
M365 Hardening Kit: Emergency Top 10 — progress
All figures are formulas over 'Project plan'. 'Not applicable' rows are excluded from % complete.
By area
Area | Controls | Done | In progress | Blocked | Not applicable | % complete | Overdue | Hours left
Identity & access (Entra ID)
Exchange Online & email security
Audit & governance
Total
By sprint
Sprint | Controls | Done | In progress | Blocked | Not applicable | % complete | Overdue | Hours left
Sprint 1 - Emergency
Total

## Project plan
ID | Control | Area | Sprint | Priority | Effort (guide) | Effort (h) | Licence | Owner | Start | Due | Status | Done date | % complete | Overdue | Verify (done when…) | Notes
E01 | Create two break-glass (emergency access) accounts | Identity & access (Entra ID) | Sprint 1 - Emergency | Highest | 30 min | 0.5 | Any |  |  |  | To do |  |  |  | Both accounts exist, are excluded from all CA policies and a sign-in alert fires on a test sign-in.
E02 | Require MFA for all users | Identity & access (Entra ID) | Sprint 1 - Emergency | Highest | 1-2 h | 2 | Free (Security defaults) or Entra ID P1 (Conditional Access) |  |  |  | To do |  |  |  | Sign-in logs show MFA satisfied for interactive sign-ins; no user is excluded except break-glass accounts.
E03 | Block legacy authentication | Identity & access (Entra ID) | Sprint 1 - Emergency | Highest | 1 h | 1 | Entra ID P1 (or Security defaults) |  |  |  | To do |  |  |  | A Conditional Access policy that blocks Exchange ActiveSync + Other clients is On (state: enabled), or Security defaults are enabled; and Entra sign-in logs show no successful legacy-auth sign-ins in the last 7 days.
E04 | Reduce and separate admin accounts | Identity & access (Entra ID) | Sprint 1 - Emergency | High | 1-2 h | 2 | Any (PIM needs Entra ID P2) |  |  |  | To do |  |  |  | 2-4 Global Admins, all cloud-only, none used for daily email.
E05 | Restrict user consent to applications | Identity & access (Entra ID) | Sprint 1 - Emergency | High | 30 min | 0.5 | Any |  |  |  | To do |  |  |  | User consent setting is restricted and the admin consent workflow is on.
E06 | Confirm audit logging is on | Audit & governance | Sprint 1 - Emergency | High | 15 min | 0.25 | Any (retention depends on license) |  |  |  | To do |  |  |  | An audit search returns events from the last 24 hours.
E07 | Block automatic external email forwarding | Exchange Online & email security | Sprint 1 - Emergency | High | 30 min | 0.5 | Exchange Online |  |  |  | To do |  |  |  | A test inbox rule forwarding to an external address is blocked; no unapproved forwarding remains.
E08 | Apply the Standard preset security policy | Exchange Online & email security | Sprint 1 - Emergency | High | 30 min | 0.5 | EOP (Defender for Office 365 for Safe Links/Attachments) |  |  |  | To do |  |  |  | Preset policy shows On and covers all recipients.
E09 | Set up SPF, DKIM and DMARC | Exchange Online & email security | Sprint 1 - Emergency | High | 1 h + DNS wait | 1 | Any |  |  |  | To do |  |  |  | A message header shows spf=pass, dkim=pass, dmarc=pass.
E10 | Self-service password reset with banned passwords | Identity & access (Entra ID) | Sprint 1 - Emergency | Medium | 1 h | 1 | Entra ID P1 for SSPR with on-prem writeback and custom banned list |  |  |  | To do |  |  |  | A test user can reset a password with two methods; a banned password is rejected.
Formulas:
Overdue = IF(AND(ISNUMBER([Due]),[Due]<TODAY(),[Status]<>"Done",[Status]<>"Not applicable"),"Yes","")